## Instruction
Fill in instruction
The first time
Fill in the name of the project and the class and group in the tab "Total"
Also with the names of the 4 students
Need more activity lines in a week?
Make a copy of the last activity line and insert that before the totals line

## Total
Time tracking |  | Hours report | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Total
Project : | The Frog - Sprint 1 | Kiarash Delavar | 5 | 2 | 2
|  | Kian Kamphuis | 2 | 2 | 5
Class-group : | Class DHI1V.SP | Emran Mohammadi | 2 | 2 | 4
|  | Max De Croon | 1 | 3 | 3
|  | Max De Croon | 4 | 5 | 5 | 4 | 3 | 0 | 3 | 8 | 32
| Group 3 | Elham Dawlati | 2 | 2 | 2
|  | Weekly total | 11 | 11 | 16
|  | Sprint total | 11 | 11 | 16
Available hours per week : | 50 | Cumulative total | 139 | 128 | 112
|  | Cumulative available | 150 | 100 | 50

## Week (1)
Week 1 | TOTAL Hours
Kiarash Delavar | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Creating the Card class and figuring out it's functions |  | 1 |  |  |  |  | 1
Sorting all the cards |  |  |  |  | 4 |  | 4
0
0
0
Total | 0 | 1 | 0 | 0 | 4 | 0 | 5
Kian Kamphuis | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Creating and displaying 5 cards | [6 empty] | 0
Finding and implementing the music tracks for the menu and the main game |  |  |  | 1 |  | 3 | 4
0
0
0
Total | 0 | 0 | 0 | 1 | 0 | 3 | 4
Emran Mohammadi | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Creating the Card class and figuring out it's functions |  | 1 |  |  |  |  | 1
Creating an array to hold out to all the cards and reading cards from images |  |  | 2 |  |  |  | 2
Creating and displaying 5 cards |  |  |  | 1 |  |  | 1
0
0
Total | 0 | 1 | 2 | 1 | 0 | 0 | 4
Max De Croon | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Creating animation for starting of the game |  |  |  | 4 |  |  | 4
0
0
0
0
Total | 0 | 0 | 0 | 4 | 0 | 0 | 4

## Week (2)
Week 2 | TOTAL Hours
Kiarash Delavar | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Creating a choosing a random king | 2 | [5 empty] | 2
Calling action for the king | 2 | [5 empty] | 2
Calling action for the minister |  |  |  | 4 |  |  | 4
0
0
Total | 4 | 0 | 0 | 4 | 0 | 0 | 8
Kian Kamphuis | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Creating a background for the start menu of the game |  |  | 2 |  |  |  | 2
Creating a background for the main game |  |  |  | 2 |  |  | 2
Writing each player's name on the table |  |  |  |  | 1 |  | 1
0
0
Total | 0 | 0 | 2 | 2 | 1 | 0 | 5
Emran Mohammadi | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Displaying the rest of the cards ( players except us ) |  | 3 |  |  |  |  | 3
Calling action for the minister |  |  |  | 4 |  |  | 4
0
0
0
Total | 0 | 3 | 0 | 4 | 0 | 0 | 7
Max De Croon | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Creating characters and backgrounds for the cutscenes | 3 | [5 empty] | 3
Creating a background for the start menu of the game |  |  | 2 |  |  |  | 2
0
0
0
Total | 3 | 0 | 2 | 0 | 0 | 0 | 5

## Week (3)
Week 3 | TOTAL Hours
Kiarash Delavar | Hours
Mahta Atiabi | Mo | Tu | We | Th | Fr | Sa/Su | Total
Doing programming for the first round of the game |  | 2 | 3 | 3 |  |  | 8
Creating a score system |  |  |  |  | 3 |  | 3
0
0
0
Total | 0 | 2 | 3 | 3 | 3 | 0 | 11
Kian Kamphuis | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Setting card number indicators for player 1 |  | 2 |  |  |  |  | 2
Creating the pictures of the round win/loose |  |  | 1 |  |  |  | 1
figuring out how to set up the music |  |  |  |  | 5 |  | 5
0
0
Total | 0 | 2 | 1 | 0 | 5 | 0 | 8
Emran Mohammadi | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Setting card number indicators for player 1 |  | 2 |  |  |  |  | 2
Creating a score system |  |  |  |  | 3 |  | 3
0
0
0
Total | 0 | 2 | 0 | 0 | 3 | 0 | 5
Max De Croon | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
turning the intro of the game to the animation | 4 | [5 empty] | 4
Designing the template of our documentation |  |  | 1 |  |  |  | 1
0
0
0
Total | 4 | 0 | 1 | 0 | 0 | 0 | 5

## Week (4)
Week 4 | TOTAL Hours
Kiarash Delavar | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Doing programming of upcoming rounds |  | 3 | 2 | 2 |  | 3 | 10
0
0
0
0
Total | 0 | 3 | 2 | 2 | 0 | 3 | 10
Kian Kamphuis | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Deploying a sound effect for throwing the cards |  |  |  |  | 4 |  | 4
0
0
0
0
Total | 0 | 0 | 0 | 0 | 4 | 0 | 4
Emran Mohammadi | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Finding and coding the king's and minister's symbol | [5 empty] | 4 | 4
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 4 | 4
Max De Croon | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Finalizing the tutorial and the menu of the game |  |  |  | 4 |  |  | 4
0
0
0
0
Total | 0 | 0 | 0 | 4 | 0 | 0 | 4

## Week (5)
Week 5 | TOTAL Hours
Kiarash Delavar | Uren
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Improving the playing of all the players except us |  |  |  | 4 |  |  | 4
Re-showing the deck of card after playing |  |  |  |  | 3 |  | 3
Making our teammate more intelligent |  |  | 4 |  |  |  | 4
0
0
Total | 0 | 0 | 4 | 4 | 3 | 0 | 11
Kian Kamphuis | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Creating the "Content documentation" |  |  |  |  | 3 |  | 3
0
0
0
0
Total | 0 | 0 | 0 | 0 | 3 | 0 | 3
Emran Mohammadi | Uren
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Improving playing of all players except us |  |  |  | 4 |  |  | 4
0
0
0
0
Total | 0 | 0 | 0 | 4 | 0 | 0 | 4
Max De Croon | Uren
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Re-showing the deck of cards after playing |  |  |  |  | 3 |  | 3
0
0
0
0
Total | 0 | 0 | 0 | 0 | 3 | 0 | 3

## HOLIDAYS
Week 6 | TOTAL Hours
Kiarash Delavar | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kian Kamphuis | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emran Mohammadi | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Max De Croon | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (7)
Week 7 | TOTAL Hours
Kiarash Delavar | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Improving player 2 and player 4 intelligence |  |  |  | 2 | 2 |  | 4
Working on ending of the game | [5 empty] | 1 | 1
0
0
0
Total | 0 | 0 | 0 | 2 | 2 | 1 | 5
Kian Kamphuis | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Working on documantation |  |  | 3 |  |  |  | 3
0
0
0
0
Total | 0 | 0 | 3 | 0 | 0 | 0 | 3
Emran Mohammadi | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Improving player 2 and player 4 intelligence |  |  |  | 2 | 2 |  | 4
Working on ending of the game | [5 empty] | 1 | 1
0
0
0
Total | 0 | 0 | 0 | 2 | 2 | 1 | 5
Max De Croon | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Working on documantation |  |  |  |  | 3 |  | 3
0
0
0
0
Total | 0 | 0 | 0 | 0 | 3 | 0 | 3

## Week (8)
Week 8 | TOTAL Hours
Kiarash Delavar | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Debuging the game and fixing flaws |  |  |  | 5 |  |  | 5
Completing the turorial and making it playable |  |  |  | 3 |  |  | 3
0
0
0
Total | 0 | 0 | 0 | 8 | 0 | 0 | 8
Kian Kamphuis | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Adjusting the volume of the game with "Audacity" | 2 | [5 empty] | 2
Designing the poster of the game |  | 3 |  |  |  |  | 3
0
0
0
Total | 2 | 3 | 0 | 0 | 0 | 0 | 5
Emran Mohammadi | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Finializing the timetable |  |  |  |  | 1 |  | 1
Debuging the game and fixing flaws |  |  |  | 5 |  |  | 5
0
0
0
Total | 0 | 0 | 0 | 5 | 1 | 0 | 6
Max De Croon | Hours
Activity description/ user story | Mo | Tu | We | Th | Fr | Sa/Su | Total
Completing the tutorial and making it playable |  |  |  | 3 |  |  | 3
Working on the documentation |  |  |  |  | 5 |  | 5
0
0
0
Total | 0 | 0 | 0 | 3 | 5 | 0 | 8